## Slide 1
THE 120 · TORONTO — BRIEFING FOR INVESTORS & ADVISORS
Eight weeks to fill the 120.
The summer go-to-market sprint: 200 interested families and 48–55 refundable $250 deposits by September 1 — so September fills the calendar on its own, and all 120 seats are committed by September 30.
JUL 13 – SEP 4, 2026 · TORONTO · PETER KUPERMAN, FOUNDER

## Slide 2
01 CONTEXT
What The 120 is
A selective network of Toronto's 120 best and brightest students, grades 3–8, in five groups — Scholars, Athletes, Makers, Founders, Givers. Members keep their current school; The 120 is what school can't give them.
01
The Network
A Tin Can and The 120 Address Book — a screen-free bat phone to 119 true intellectual peers across the city, plus in-person gatherings all year.
02
The Project
One super-interesting, year-long project per member — mentored, shipped, and demoed live at quarterly Toronto intensives. First one: Oct 31–Nov 1.
03
The Subject
Super advanced in 1–2 academic subjects on the GT / TimeBack platform — mastery-based, no ceiling, with a weekly 1:1 academic advisor.
120
SEATS, TOTAL
3–8
GRADES
3–5
HRS / WEEK
$3,000
ANNUAL MEMBERSHIP
Mid Sept
KICK-OFF EVENT
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
02

## Slide 3
02 THE GOAL
Sell the summer, so September sells itself
200
CONSENTED FAMILIES BY SEPT 1
CASL-consented emails in the system — accounts, RSVPs, opt-ins. One number the whole funnel hangs off.
48–55
$250 DEPOSITS BY SEPT 1
Paid on live Stripe, verified. Real committed seats — and a truthful live seat count for the September push.
120
SEATS COMMITTED BY SEPT 30
The hard goal: all 120 seats (113 open today) committed, with a waitlist behind them.
“$250, fully refundable until Sept 30. The only thing you can lose is the seat.”
THE RISK REVERSAL —
HONEST, HIGH-CONVICTION,
IN EVERY PITCH
OPERATOR REALITY: SOLO FOUNDER + TWO DEVS ON TICKETS · ~20 GTM HOURS/WEEK · 10 CALLS/WEEK
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
03

## Slide 4
03 THE FUNNEL MATH
The math that fills the seats
Interested families (consented)
200
Account + child dossier started
110 55%
Dossier submitted
77 70%
Intro call booked
90 45%
Call held
72 80% show
$250 deposit paid
48–55 ~60%
REALITY CHECKS
29 new leads/week over 7 active weeks. 10 calls/week ≈ 2 a day — sustainable solo. 48–55 deposits leaves ~60 seats for the September machine.
THE TRIPWIRE
Any stage running 30% under plan for two weeks becomes the next week's primary push — regardless of plan.
WEEK 1 UNBLOCKS
Stripe live keys, the booking link, and an email provider don't exist yet. No real deposit can be taken until they ship — Week 1 exists to fix all three.
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
04

## Slide 5
04 THE PLAN AT A GLANCE
Four phases. One verb each.
ARM
W1–2 · JUL 13–26
Build the machine; ignite the warm network.
40 INTERESTED · 20 CALLS BOOKED
→
SEED
W3–4 · JUL 27–AUG 9
Plant in the communities where the 120 already hang out.
105 INTERESTED · FIRST 15 DEPOSITS
→
SURGE
W5–6 · AUG 10–23
Go vertical on the five groups, then gather everyone.
170 INTERESTED · 32 DEPOSITS
→
LAND
W7–8 · AUG 24–SEP 4
Convert deposits; hand off to September.
200+ INTERESTED · 48–55 DEPOSITS
THE CONSTANT WEEKLY RHYTHM
MON pick the one push, send the week's email TUE–THU two calls a day + the push FRI metrics vs. the funnel, thank-yous, shout-outs
CADENCE AND NAMED PHASES BORROWED FROM FOUNDERS.SCHOOL'S “YEAR IN DETAIL” — NEVER MORE THAN ONE PRIMARY PUSH PER WEEK
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
05

## Slide 6
05 WEEK BY WEEK — FIRST HALF
Arm the machine, then seed the communities
PHASE 1 — ARM JUL 13–26
PHASE 2 — SEED JUL 27–AUG 9
W1 · JUL 13–19
Machine online + the warm 25
Stripe goes live, the booking link ships, the email provider gets wired. Personal notes — not blasts — to the 25 warmest families. The one-page explainer PDF ships.
25 WARM CONVOS · 10 CALLS BOOKED · MACHINE LIVE
W2 · JUL 20–26
Recruit the ambassadors
12–15 grade 7/8 Founding Ambassadors recruited through the kids' own networks; one virtual kickoff with kids and parents; referral codes issued; the Gauntlet tournament soft-launches to seed the leaderboard.
12 AMBASSADORS · 40 INTERESTED CUM.
W3 · JUL 27–AUG 2
Gifted-parent communities
Value-first founder posts (real TimeBack data, real kids) in Ontario gifted-parent groups and ABC Ontario chapters — PDF by DM, never cold links. Three “120 coffees” with connector parents.
70 INTERESTED CUM. · 30 CALLS BOOKED
W4 · AUG 3–9
The Gauntlet goes public
A 3-week public leaderboard tournament in grade bands, weekly boss themes. Winners earn a permanent Founding Leaderboard spot and first demo slot at the October intensive. Kids recruit kids.
105 INTERESTED CUM. · FIRST 15 DEPOSITS
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
06

## Slide 7
06 WEEK BY WEEK — SECOND HALF
Surge on the five groups, then land the deposits
PHASE 3 — SURGE AUG 10–23
PHASE 4 — LAND AUG 24–SEP 4
W5 · AUG 10–16
Five-group verticals
One tailored outreach per group: Scholars via math-contest circles, Athletes via rep-team parent reps, Makers via arts programs, Founders via kid-entrepreneur fairs, Givers via community orgs. Organizers forward — we never blast their lists.
140 INTERESTED CUM. · 22 DEPOSITS CUM.
W6 · AUG 17–23
Info sessions week
Two 45-minute virtual info sessions plus one in-person Toronto meetup — kids play the Gauntlet live on a projector while parents talk. Every RSVP is a consented lead; every attendee gets a next-day recap and booking link.
170 INTERESTED CUM. · 32 DEPOSITS CUM.
W7 · AUG 24–30
The deposit push
The back-to-school moment: a 3-email sequence, personal calls to every submitted-dossier family, and a truthful live seat count. Families deposited by Sept 1 are named the Founding 120 at the October intensive.
190 INTERESTED CUM. · 45 DEPOSITS CUM.
W8 · AUG 31–SEP 4
September landing
Hand-off week: nurture automation verified end-to-end, ambassador back-to-school kits delivered, waitlist copy ready, 12 call slots a week open through October, and the “year begins” email goes out.
200+ INTERESTED · 48–55 DEPOSITS · 20+ SEPT CALLS PRE-BOOKED
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
07

## Slide 8
07 THE BIGGEST ORGANIC CHANNEL
Kids are the engine, not the audience
12–15 grade 7/8 ambassadors
× 3–5 genuinely interested families each
= 40–70 leads
GRADE 7/8 KIDS ARE THE MOST NETWORKED — AND MOST CREDIBLE — VOICE TO OTHER KIDS
01
Challenge friends to the Gauntlet — Their referral code rides on every shared score card.
02
Bring one family to an info session — Or to the August in-person Toronto meetup.
03
Give a 2-minute “why I'm in” — Kid voice sells better than any deck — including this one.
04
Show off the Tin Can — The bat phone is a physical, enviable object.
THE ETHICS LINE
Recognition, never cash. No per-signup payments to minors, no quotas, parent consent on everything — and CASL-clean: leads only arrive when a family acts themselves. Tracking is one referral-code field and a Friday tally; no extra tooling.
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
08

## Slide 9
08 WHERE THE LEADS COME FROM
Five channels, ranked by leverage
01
Gauntlet Summer Tournament
Public leaderboard sprint on the free math trainer — the only channel where the product markets itself to the actual member. Kids recruit kids.
EFFORT
MED
IMPACT
HIGH
02
Ontario gifted-parent communities
ABC Ontario chapters, gifted/IEP parent groups, Toronto parenting threads. Exactly the top-1–2% parent, already searching for this.
EFFORT
LOW
IMPACT
MED-HIGH
03
Math-contest ecosystem
CEMC / Math Kangaroo parent circles and math-circle coaches. A pre-qualified Scholars pipeline — contest parents pay for acceleration.
EFFORT
MED
IMPACT
HIGH
04
Rep-sports & arts verticals
One parent-rep per rep team, one director per arts program forwards the one-pager. Athletes and Makers seats won't fill from math channels.
EFFORT
MED
IMPACT
MED
05
“120 Coffees”
Three coffees a week with Toronto connector-parents; each one ends with an ask for two introductions. Deposits at this price close on trust.
EFFORT
HIGH
IMPACT
HIGH
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
09

## Slide 10
09 THE HAND-OFF
September 1 — definition of done
✓
200+ consented families
In the email system, tagged by stage and source.
✓
48+ deposits paid
Live Stripe, verified; ~58–65 seats showing — real scarcity.
✓
Booking link open
12 slots/week through October; 20+ September calls pre-booked.
✓
Nurture running
Automated sequences fill the calendar by themselves.
✓
Ambassadors back in school
12–15 kids with kits, codes, and a September Gauntlet season.
✓
Intensive #1 sellable
Oct 31–Nov 1 date and city in all copy; venue locked internally.
✓
Waitlist mechanics ready
Copy, form, and admin flow for when groups fill — Scholars caps first.
THE NURTURE MACHINE
Five automated sequences — account created, dossier submitted, call held, deposit paid, stalled 14 days. Every email ends with one CTA: book the call or finish the dossier.
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
10

## Slide 11
10 THE ASKS
Where I need your wisdom
The plan is honest about what it doesn't know. These five decisions are where an hour of your experience is worth more than a month of mine.
ASK 01
Intensive #1 venue
Mid-Sept Kick-Off event is the closing argument in every call and email. Venue leads in Toronto, e.g. spaces, schools, partners need to get figured out.
ASK 02
Admissions ops
Who reviews dossiers, on what SLA, and is the assessment ready before deposits pile up? A 48-deposit pipeline with no assessment path is a refund machine.
ASK 03
Pricing on calls
The plan sells the $3,000 Membership everywhere and up-sells the $15,000 Full Academic Core on the call. Is that still the right play?
ASK 04
Introductions
Connector parents, rep-team coaches, camp directors, heads of gifted programs. Also Private Ski Club lists. Every warm introduction compounds — one is a genuine gift.
ASK 05
Seat policy per group
With 5 groups, should we do ~24 seats per group? Scholars may oversubscribe first so do extra Scholars wait-list, get steered to another group or do we overweight?
THE 120 · GT TORONTO
SUMMER GTM SPRINT · JUL–SEP 2026
11

## Slide 12
THE 120 · GT TORONTO
Help me fill the 120.
The plan is built and the machine goes live Monday, July 13. What compounds fastest now is trust — and trust travels through people like you.
01
One introduction: to a connector parent, coach, or program director.
02
One hour of advice : on any of the five asks, i.e. venue, admissions, pricing, intros, seats.
03
One forward : of the one-pager to a family you'd personally vouch for.
PETER KUPERMAN · PKUPERMAN@GMAIL.COM · THE120.SCHOOL