## Week 1 Scorecard
THE 120 — WEEK 1 SCORECARD (Jul 13–19, 2026)
Phase 1 · ARM · Primary push: “Machine online + warm 25” · Grade: strong — machine live, warm engine converting, deposits 3 weeks ahead of plan
Area | Deliverable / Target | Planned | Actual | Status | Notes / Carry-over
Machine | Cal.com booking link | Live + wired into site | Live; 1 booking from a new visitor | Done | —
Machine | Stripe go-live | Live keys + $250 charge/refund verified | Live; a real $250 deposit taken | Ahead | Deposits weren’t forecast until Week 4
Machine | Email provider + welcome #1 | Provider picked + welcome sending | Resend set up; welcome NOT sent | Partial | → Send today (Week 2)
Machine | Domain + admissions@ mailbox | Registered + live | Both registered and live | Done | —
Build | Ticket A — “how did you hear / referral code” field | Filed + shipped | Shipped & live on signup | Done | Powers all source attribution
Build | Ticket B — Gauntlet shareable score card | Ticket filed | Not started | Not started | → Build spec to Ethan (Week 2)
Assets | One-page explainer PDF | Final branded PDF | Draft | Draft | → Finalize (Week 2)
Assets | Welcome email #1 copy | Written + sending | Not sent | Partial | → Draft + send (Week 2)
Outreach | Warm-25 messaged | 25 conversations started | 26 messaged / 16 real conversations | Done | Met target on messaged
Outreach | Calls booked | 10 booked | 8 held / upcoming | Partial | 80% of target — nearly there
Ambassadors | Seed texts to families | 3 families texted | 0 — no work started | Not started | → 5 personally seeded (Week 2)
Status key: | Done / Ahead = shipped · Partial / Draft = carry into Week 2 · Not started = must be picked up

## Funnel & Sources
FUNNEL — PLAN (by Sep 1) vs. ACTUAL (end of Week 1)
Sep-1 mission: 200 interested families + 48–55 refundable deposits, so September fills itself
Stage | Sep-1 Target | End of W1 | % of Sep-1 goal | Read
Interested families (CASL-consented) | 200 | 32 | 16% | Ahead of the ~25/wk pace needed
— not yet messaged | — | 6 |  | Queue — send this week
— messaged / conversation started | — | 26 |  | Met the 25 warm-convo target
— real back-and-forth conversation | — | 16 |  | Deep warm relationships
Intro call booked | 90 | 8 | 8.889% | ~1/wk pace vs 10/wk needed later
Call held | 72 | 8 | 11.11% | Every conversation is converting
Dossier submitted | 77 | 2 | 2.597% | Early — ahead of schedule
$250 deposit paid | 50 | 1 | 2% | 3 weeks early (not due until W4)
WHERE THE FAMILIES CAME FROM
Source | Count | Share
Warm network (founder-led personal outreach) | 30 | 90.91%
Inbound — founder’s posts on X | 3 | 9.091%
Total families | 33
Note: | Families ≠ students — several families have 2+ kids, so student/seat count runs higher than 32. X inbound is unplanned and free; small n (3) but worth a deliberate test.

## 8-Week Tracker
THE 120 — 8-WEEK GTM TRACKER
Fill the yellow ACTUAL cells each Friday. Status auto-flags any week where interested runs >30% under target — the plan’s rule: that stage becomes the next week’s primary push.
Week | Phase | Dates | Primary push | Interested (cum.) |  | Calls booked (cum.) |  | Deposits (cum.) |  | Ambassadors |  | Interested vs target | Status (auto) | Notes
|  |  |  | Target | Actual | Target | Actual | Target | Actual | Target | Actual
W1 | ARM | Jul 13–19 | Machine online + warm 25 | 25 | 32 | 10 | 8 | 0 | 1 | 0 | 0 | 28% | ON TRACK / AHEAD | Strong start; deposits ahead. Carry: welcome email, share card, one-pager.
W2 | ARM | Jul 20–26 | Recruit ambassadors | 40 |  | 20 |  | 0 |  | 12 |  |  | — | Adjusted: warm engine → 10 new families; 5 ambassadors self-seeded (stretch 12–15 if Ethan leads).
W3 | SEED | Jul 27–Aug 2 | Gifted-parent communities | 70 |  | 30 |  | 0 |  | 12 |  |  | —
W4 | SEED | Aug 3–9 | The Gauntlet goes public | 105 |  | 40 |  | 15 |  | 12 |  |  | —
W5 | SURGE | Aug 10–16 | Five-group verticals | 140 |  | 55 |  | 22 |  | 12 |  |  | —
W6 | SURGE | Aug 17–23 | Info sessions week | 170 |  | 70 |  | 32 |  | 12 |  |  | —
W7 | LAND | Aug 24–30 | Deposit push | 190 |  | 85 |  | 45 |  | 12 |  |  | —
W8 | LAND | Aug 31–Sep 4 | September landing | 200 |  | 90 |  | 50 |  | 15 |  |  | —
How to use: | Yellow = you fill each Friday (cumulative running totals). Targets come straight from the sprint plan §1–§2. Deposits are cumulative and only start mounting from W4.

## Working vs Not + Actions
WHAT’S WORKING vs. WHAT’S NOT — and Week 2 actions
Read after Week 1; drives the Week 2 plan
✓ WORKING — double down
Warm network conversion | 10 messaged → 8 conversations → 8 calls booked (~80% message→call). Deposits close on trust; trust closes on a call — validated.
The machine shipped | Booking, live Stripe payments, attributed signups, and domain all live in week 1.
Ahead on hard stages | 1 real deposit + 2 dossiers already — the plan didn’t forecast deposits until Week 4.
Free inbound from X | 3 strangers signed up from the founder’s own X posts — a channel that isn’t in the plan and costs nothing.
✗ NOT WORKING / BEHIND — fix in Week 2
Ambassadors at zero | Week 2’s whole push was 12–15 ambassadors. No work started; ownership (Ethan) unconfirmed.
Ambassador tooling missing | The viral mechanic — the Gauntlet share card — isn’t built, so even a recruited crew has nothing to share yet.
Welcome email not sending | Resend is set up but welcome #1 hasn’t gone — the nurture machine isn’t running.
One-pager still a draft | The core sales asset every ‘tell me more’ reply needs isn’t finalized.
Warm list under-built | Only ~16 named / 26 messaged vs. a 25+ list — the highest-ROI channel is under-fed.
WEEK 2 ACTIONS & DELIVERABLES
Action / Deliverable | Detail | Owner
Warm engine → 10 new families | Message the 6 unsent, rebuild list past 25, ask 8 warm families for 2 intros each | Peter
Seed 5 ambassadors personally | From warm families; floor of 5 (stretch 12–15 if Ethan leads) | Peter
Decide Ethan as ambassador lead | Know by tomorrow; if no, big push slides to W3 (decide next Monday) | Peter
Send welcome email #1 | Turn on the nurture machine today | Peter
Finalize the one-pager | Ship the branded PDF from the draft | Claude → Peter
Gauntlet share-card build spec | Full spec: what it is, behaviour, how it works, tech notes — for Ethan | Claude → Ethan
Pipeline stages update spec | Add Conversation → Call Booked → Call Held before Dossier Submitted | Claude → Ethan
Ambassador kit | 1-page ‘what you do’, referral-code card, shareable images, parent consent note | Claude
Ambassador kickoff agenda | 45-min virtual kickoff run-of-show for the seeded ambassadors | Claude