## Slide 1
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
Eight weeks to fill
the 120 — week by week.
The summer go-to-market sprint in full detail: every marketing activity, every week, and how each one delivers 200 interested families and 48–55 refundable $250 deposits by September 1 — so September fills the calendar on its own, and all 120 seats are committed by September 30.
Shared so The Notable Group can propose where its capabilities compound the plan.
JUL 13 – SEP 4, 2026 · TORONTO · PETER KUPERMAN, FOUNDER

## Slide 2
01 CONTEXT
What The 120 is
A selective network of Toronto's 120 best and brightest students, grades 3–8, in five groups — Scholars, Athletes, Makers, Founders, Givers. Members keep their current school; The 120 is what school can't give them.
01
The Network
A Tin Can and The 120 Address Book — a screen-free bat phone to 119 true intellectual peers across the city, plus in-person gatherings all year.
02
The Project
One super-interesting, year-long project per member — mentored, shipped, and demoed live at quarterly Toronto intensives. First one: Oct 31–Nov 1.
03
The Subject
Super advanced in 1–2 academic subjects on the GT / TimeBack platform — mastery-based, no ceiling, with a weekly 1:1 academic advisor.
120
SEATS, TOTAL
3–8
GRADES
3–5
HRS / WEEK
$3,000
ANNUAL MEMBERSHIP
Mid Sept
KICK-OFF EVENT
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
02

## Slide 3
02 THE GOAL
Sell the summer, so September sells itself
200
CONSENTED FAMILIES BY SEPT 1
CASL-consented emails in the system — accounts, info-session RSVPs, opt-ins. One number the whole funnel hangs off: ~29 new families a week for 7 active weeks.
48–55
$250 DEPOSITS BY SEPT 1
Paid on live Stripe, verified. Real committed seats — and a truthful live seat count that powers the September urgency push.
120
SEATS COMMITTED BY SEPT 30
The hard goal: all 120 seats (113 open today) committed, with a waitlist behind them. September's nurture machine closes the last ~60.
“$250, fully refundable until Sept 30. The only thing you can lose is the seat.”
THE RISK REVERSAL —
HONEST, HIGH-CONVICTION,
IN EVERY PITCH, EVERY WEEK
OPERATOR REALITY: SOLO FOUNDER + TWO DEVS ON TICKETS · ~20 GTM HOURS/WEEK · 10 CALLS/WEEK · ONE PRIMARY PUSH PER WEEK, NEVER MORE
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
03

## Slide 4
03 THE FUNNEL MATH
The math that fills the seats
Interested families (consented)
—
200
Account + child dossier started
55% OF INTERESTED
110
Dossier submitted
70% OF STARTED
77
Intro call booked
45% OF INTERESTED
90
Call held (no-show ~20%)
80% OF BOOKED
72
$250 deposit paid
~60% OF HELD CALLS
48–55
REALITY CHECKS
29 leads/week — 200 over 7 active weeks.
10 calls/week — 2 a day, sustainable solo.
48–55 deposits leaves ~60 September seats — fed by nurture, evangelist parents, back-to-school urgency.
THE TRIPWIRE
Any stage running 30% under plan for two weeks becomes the next week's primary push — regardless of plan.
WEEK-1 BLOCKERS: STRIPE IS TEST-MODE · NO BOOKING LINK · NO EMAIL PROVIDER. NO DEPOSIT CAN BE TAKEN UNTIL ALL THREE SHIP — WEEK 1 FIXES THEM.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
04

## Slide 5
04 THE PLAN AT A GLANCE
Four phases. One verb each. One push per week.
ARM
W1–2 · JUL 13–26
Build the machine; ignite the warm network and recruit kid ambassadors.
40 INTERESTED · 20 CALLS BOOKED
SEED
W3–4 · JUL 27–AUG 9
Plant in the communities where the 120 already hang out; the Gauntlet goes public.
105 INTERESTED · FIRST 15 DEPOSITS
SURGE
W5–6 · AUG 10–23
Go vertical on the five groups, then gather everyone at info sessions.
170 INTERESTED · 32 DEPOSITS
LAND
W7–8 · AUG 24–SEP 4
Convert deposits on the back-to-school moment; hand off to September.
200+ INTERESTED · 48–55 DEPOSITS
THE CONSTANT WEEKLY RHYTHM — SAME CADENCE, ALL EIGHT WEEKS
MON pick the one push, send the week's email
TUE–THU two calls a day + the push
FRI metrics vs. the funnel, thank-yous, ambassador shout-outs
CADENCE AND NAMED PHASES BORROWED FROM FOUNDERS.SCHOOL'S “YEAR IN DETAIL” — NEVER MORE THAN ONE PRIMARY PUSH PER WEEK
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
05

## Slide 6
05 WEEK 1 OF 8 · PHASE 1 — ARM · JUL 13–19
The one push: Machine online + the warm 25
THE WEEK'S WORK
01 Go live on the machine — Cal.com booking link created and wired to every Book-a-call button; Stripe moves from test mode to live keys with one real $250 charge/refund verified; email provider picked (Resend / Customer.io) and welcome email #1 wired.
02 Instrument attribution — dev ticket for a “How did you hear about us? / referral code” field on account creation, so every later channel is measurable from day one.
03 Message the 25 warmest contacts — UTS circles, the 7 founding families, /parents story families. Personal notes and coffees, never blasts.
04 Open the pipeline — 10 intro calls booked from the warm list before Sunday.
SHIPS THIS WEEK
One-page explainer PDF — five groups, $3,000 membership, refundable $250 deposit, Oct 31 intensive — plus welcome email #1.
CHANNELS
Personal email and text · coffees · no paid, no broadcast
SCOREBOARD BY FRIDAY
25
WARM CONVOS STARTED
10
CALLS BOOKED
LIVE
STRIPE · BOOKING · EMAIL
WHY THIS WEEK
DELIVERS THE GOAL
Nothing in this plan can convert until this week ships: booking, payments and email are the rails every later week runs on — and the warm 25 seed the first 10 of the 90 calls the funnel needs.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
06

## Slide 7
06 WEEK 2 OF 8 · PHASE 1 — ARM · JUL 20–26
The one push: Recruit the kid ambassadors
THE WEEK'S WORK
01 Recruit 12–15 grade 7/8 ambassadors through the founder's kids' network and friends-of-friends — the most networked, most credible voices to other kids.
02 One 45-minute virtual kickoff with the kids plus a parent each; referral codes issued (AMB-FIRSTNAME, tracked in the how-did-you-hear field).
03 Soft-launch the Gauntlet Summer Tournament to ambassadors only — seed the leaderboard before it opens to the public in Week 4.
04 Compound the warm network — ask each of Week 1's warm families for two introductions.
SHIPS THIS WEEK
Ambassador kit — one-page “what you do,” referral code card, 3 shareable Gauntlet images, and a plain-language parent consent note.
CHANNELS
DM / text via parents · one Zoom kickoff
SCOREBOARD BY FRIDAY
12–15
AMBASSADORS ONBOARD
20
CALLS BOOKED, CUM.
40
INTERESTED, CUM.
WHY THIS WEEK
DELIVERS THE GOAL
The single biggest organic channel in the plan: 12–15 grade-7/8 kids × 3–5 genuinely interested families each = 40–70 of the 200 leads. Kids are the engine, not the audience.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
07

## Slide 8
07 WEEK 3 OF 8 · PHASE 2 — SEED · JUL 27–AUG 2
The one push: Gifted-parent communities
THE WEEK'S WORK
01 Value-first founder posts — the real TimeBack story from /parents, real data, real kids — in Ontario gifted/enrichment Facebook groups and ABC (Association for Bright Children) Ontario chapters.
02 Earn, never blast — no cold links in no-promo groups; answer questions in-thread and DM the explainer PDF on request.
03 Show up where GTA parents ask — Reddit r/askTO and r/ontario parenting threads, same value-first rules.
04 Three “120 coffees” with connector parents — school-council chairs, camp directors — each one ends with an ask for two introductions.
SHIPS THIS WEEK
/parents story post — a 300-word founder narrative, no hype, link at the end — plus 5 canned answers to the most common objections.
CHANNELS
Facebook groups · ABC Ontario · Reddit · coffees
SCOREBOARD BY FRIDAY
70
INTERESTED, CUM. (+30)
30
CALLS BOOKED, CUM.
3
CONNECTOR COFFEES
WHY THIS WEEK
DELIVERS THE GOAL
These communities are exactly the top-1–2% parent, already searching for this — the lowest-cost lead source in the plan, and the one that keeps the 29-leads-a-week rate on track.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
08

## Slide 9
08 WEEK 4 OF 8 · PHASE 2 — SEED · AUG 3–9
The one push: The Gauntlet goes public
THE WEEK'S WORK
01 Open the Gauntlet Summer Tournament to everyone — a 3-week public leaderboard sprint, grade bands 3–4 / 5–6 / 7–8, weekly “boss week” themes.
02 Make winning matter — winners earn a named spot on a permanent Founding Leaderboard plus the first demo slot at the October intensive.
03 Put the kids to work — ambassadors challenge classmates with their codes; parents share scores (“free math game a Toronto founder built”).
04 Ship the funnel surface — /gauntlet landing with a parent-facing banner into the join flow; dev ticket for an auto-generated shareable score card.
SHIPS THIS WEEK
Gauntlet share card (auto-generated score image) + tournament rules page + weekly leaderboard email.
CHANNELS
Kid word-of-mouth · ambassador shares · parent groups
SCOREBOARD BY FRIDAY
105
INTERESTED, CUM. (+35)
40
CALLS BOOKED, CUM.
15
FIRST DEPOSITS
WHY THIS WEEK
DELIVERS THE GOAL
The only channel where the product markets itself to the actual member — kids recruit kids while parents see a serious math trainer. And the first 15 deposits prove the funnel end to end.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
09

## Slide 10
09 WEEK 5 OF 8 · PHASE 3 — SURGE · AUG 10–16
The one push: Five-group verticals
THE WEEK'S WORK
01 Scholars — CEMC/Waterloo contest and Math Kangaroo parent communities, math-circle coaches: the Gauntlet as free FastMath training, The 120 as the year-round home.
02 Athletes — rep/AAA team parent reps (GTHL, rep soccer, competitive swim): “your kid already trains like a pro at sport — this is that, for everything else.”
03 Makers · Founders · Givers — arts-program lists (RCM, youth film/maker camps); kid-entrepreneur fairs and DECA-adjacent parents; youth-volunteering and faith/community orgs.
04 CASL-clean distribution — coaches and organizers forward to their own lists; we never blast them. Their consent relationship, not ours.
SHIPS THIS WEEK
Five one-page group sheets — same skeleton, one hero line each (e.g. “Train seriously, compete seriously, and think like a pro”).
CHANNELS
Coaches · program directors · contest-parent groups
SCOREBOARD BY FRIDAY
140
INTERESTED, CUM. (+35)
55
CALLS BOOKED, CUM.
22
DEPOSITS, CUM.
WHY THIS WEEK
DELIVERS THE GOAL
Athletes, Makers, Founders and Givers seats will never fill from math channels. One tailored outreach per group balances the five groups — so all 120 seats fill, not just Scholars.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
10

## Slide 11
10 WEEK 6 OF 8 · PHASE 3 — SURGE · AUG 17–23
The one push: Info sessions week
THE WEEK'S WORK
01 Two 45-minute virtual info sessions (Tue evening, Sat morning): 15 min founder story → 15 min the year in detail (project → quarterlies → Oct 31 demo) → 15 min Q&A — ending on the refundable-deposit offer.
02 One in-person Toronto meetup — park or rec-room; kids play the Gauntlet live on a projector while parents talk to the founder.
03 Ambassadors each bring one family and give a 2-minute “why I'm in” — kid voice sells better than any deck.
04 Follow-up machine — every attendee gets a next-day recap email with the booking link.
SHIPS THIS WEEK
10-slide info-session deck + RSVP page (Luma/Eventbrite) + next-day recap email.
CHANNELS
Luma / Eventbrite · every prior channel invited · ambassadors
SCOREBOARD BY FRIDAY
170
INTERESTED, CUM. (+30)
70
CALLS BOOKED, CUM.
32
DEPOSITS, CUM.
WHY THIS WEEK
DELIVERS THE GOAL
The week every prior channel funnels into one room. Every RSVP is a consented lead, every attendee gets a next-day recap and booking link — the bridge that turns breadth into booked calls and deposits.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
11

## Slide 12
11 WEEK 7 OF 8 · PHASE 4 — LAND · AUG 24–30
The one push: The deposit push
THE WEEK'S WORK
01 Ride the back-to-school moment — “before the school year swallows you, reserve the seat: $250, fully refundable until Sept 30.”
02 3-email sequence to every non-depositor on the consented list; SMS only where expressly consented.
03 Personal founder call to every submitted-dossier family without a deposit.
04 Truthful scarcity — live seat count published in every email; families deposited by Sept 1 are named the Founding 120 at the October intensive.
SHIPS THIS WEEK
Deposit-push sequence (3 emails) + written deposit/refund terms page — required before pushing hard.
CHANNELS
Email sequence · personal calls · consented SMS
SCOREBOARD BY FRIDAY
190
INTERESTED, CUM. (+20)
85
CALLS BOOKED, CUM.
45
DEPOSITS, CUM.
WHY THIS WEEK
DELIVERS THE GOAL
The conversion week: back-to-school urgency meets zero risk. The whole pipeline built over six weeks gets one honest, high-pressure-free reason to commit now — and the deposit count nearly doubles.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
12

## Slide 13
12 WEEK 8 OF 8 · PHASE 4 — LAND · AUG 31–SEP 4
The one push: September landing
THE WEEK'S WORK
01 Verify the nurture automation end-to-end — five trigger sequences (account created, dossier submitted, call held/no deposit, deposit paid, stalled 14 days), every email ending on one CTA: book the call or finish the dossier.
02 Send ambassadors back to school armed — kits delivered, codes live, a September Gauntlet season announced.
03 Set the September table — waitlist copy ready, founder's calendar open at 12 call slots/week through October, weekly-metrics dashboard reviewed.
04 Send “the year begins” — intensive #1 dates (Oct 31–Nov 1) and what happens next, to the whole consented list.
SHIPS THIS WEEK
“The Year Ahead” email + waitlist page copy.
CHANNELS
Email · ambassadors in schools
SCOREBOARD BY FRIDAY
200+
INTERESTED, CUM.
48–55
DEPOSITS, CUM.
20+
SEPT CALLS PRE-BOOKED
WHY THIS WEEK
DELIVERS THE GOAL
The handoff week: the sprint becomes a machine. Nurture fills the calendar on its own, ambassadors carry it into schools, and September inherits 20+ pre-booked calls to close the last ~60 seats by Sept 30.
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
13

## Slide 14
13 THE BIGGEST ORGANIC CHANNEL
Kids are the engine, not the audience
12–15
GRADE 7/8 AMBASSADORS
× 3–5
GENUINELY INTERESTED FAMILIES EACH
= 40–70 leads
WHAT AMBASSADORS DO
01 Challenge friends to the Gauntlet — their referral code rides on every shared score card.
02 Bring one family to an info session — or to the August in-person Toronto meetup.
03 Give a 2-minute “why I'm in” — kid voice sells better than any deck, at every info session.
04 Show off the Tin Can — the bat phone is a physical, enviable object friends ask about.
INCENTIVES — RECOGNITION, NEVER CASH
Founding Ambassador title (named in the Address Book, badge at the intensive) · Gauntlet glory (permanent leaderboard flair, early boss access) · Intensive perks (first demo slot, ambassador table) · milestone shout-outs, never per-head bounties.
ETHICS + CASL: NO PAYMENTS TO MINORS · NO QUOTAS · PARENT CONSENT, OPT-OUT ANYTIME · KIDS SHARE PERSON-TO-PERSON; THE COMPANY ONLY EMAILS EXPRESS OPT-INS · LEADS ARRIVE BY THE FAMILY ACTING THEMSELVES
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
14

## Slide 15
14 THE HAND-OFF
September 1 — definition of done
✓
200+ consented families in the email system, tagged by stage and source.
✓
48+ deposits paid on live Stripe, verified — seat count showing ~58–65 left.
✓
Booking link open 12 slots/week through October; 20+ September calls booked.
✓
Automated nurture running so the calendar fills itself (sequences below).
✓
12–15 ambassadors in school with kits, codes, and a September Gauntlet season.
✓
Intensive #1 sellable Oct 31–Nov 1 date and city in all copy; venue locked.
✓
Waitlist mechanics ready copy, form and admin flow for when groups fill — Scholars will likely cap first.
THE CALENDAR-FILLING MACHINE — EVERY EMAIL ENDS ON ONE CTA: BOOK THE CALL OR FINISH THE DOSSIER
ACCOUNT CREATED
welcome → dossier nudge → founder story → book the call
DOSSIER SUBMITTED
confirmation + booking → what review looks for → founder note
CALL, NO DEPOSIT
recap + deposit link → live seat count → final personal email
DEPOSIT PAID
welcome to the Founding 120 → intensive details → referral ask
STALLED 14 DAYS
one re-engagement email, then monthly digest only
SEPTEMBER RUNS ITSELF: LABOUR-DAY “SCHOOL JUST REMINDED YOU WHY” EMAIL · MID-SEPT REFUNDABILITY COUNTDOWN (WINDOW CLOSES SEPT 30) · EVERY DEPOSITED FAMILY ASKED FOR ONE INTRODUCTION
THE 120 · TORONTO — BRIEFING FOR THE NOTABLE GROUP
SUMMER GTM SPRINT · JUL–SEP 2026
15

## Slide 16
15 THE ASK — FOR THE NOTABLE GROUP
Where would Notable compound this?
The plan is built to run on a solo founder's ~20 hours a week — and it will run regardless. What we want from The Notable Group is a proposal: across these eight weeks, where would your capabilities make the plan meaningfully bigger, faster, or louder than one founder can?
01
Awareness & PR
A Toronto founder story with real data, a $250 risk-reversal hook, and an Oct 31 demo-day moment — what earns coverage?
02
Social & digital
The Gauntlet tournament, share cards, and /parents stories — what turns organic mechanics into reach?
03
Community & influencer
Gifted-parent groups, coaches, connector parents — who amplifies credibly without breaking the value-first rules?
04
Experiential
Info sessions, the August meetup, the Oct 31–Nov 1 intensive — what makes them unmissable?
TIMING: THE SPRINT WENT LIVE JULY 13 — WEEK 1 IS ALREADY IN FLIGHT. EVERY WEEK EARLIER YOU'RE IN, THE MORE THE WORK COMPOUNDS.
PETER KUPERMAN, FOUNDER · PETER@THE120.SCHOOL